## Sheet1
Burn down chart
Sprint 1
Project | Story | Task | Start | Day 1 | Day 2 | Day 3 | Day 4
e-VMOL | Harus ada tampilan slide mengenai e-VMOL | Pembuatan Halaman Depan | 4 | 0 | 2 | 2 | 0
e-VMOL |  | Slide umum e-VMOL | 6 | 6 | 2 | 3 | 0
e-VMOL | Slide selanjutnya berisi Detail-detail dari VMOL itu sendiri | Slide Kelebihan VMOL | 5 | 0 | 2 | 2 | 0
e-VMOL |  | Slide apa itu VMOL | 5 | 0 | 3 | 3 | 0
e-VMOL | Mengedit Style CSS VMOL agar tidak kaku | Ubah Style CSS slide | 3 | 0 | 2 | 2 | 0
Ideal - Remaining effort in uninterrupted working hours |  |  | 23 | 17.25 | 11.5 | 5.75 | 0
Actual - Remaining effort in uninterrupted working hours |  |  | 23 | 6 | 11 | 12 | 0
Sprint 2
Project | Story | Task | Start | Day 1 | Day 2 | Day 3 | Day 4
e-VMOL | Isi Slide Presentasi dengan penjelasan dari slide yang terdapat point-point | Penambahan slide-slide dari Kelebihan VMOL | 4 | 2 | 1 | 1 | 0
e-VMOL | Tambah Slide VMOL yang menunjang penjelasan VMOL | Penambahan slide-slide VMOL | 5 | 3 | 2 | 2 | 0
e-VMOL | Tambah Detail terhadap Slide | Penambahan detail-detail dari VMOL | 3 | 3 | 1 | 2 | 0
e-VMOL | Edit Style CSS VMOL | Edit CSS slide VMOL | 4 | 2 | 1 | 1 | 0
Ideal - Remaining effort in uninterrupted working hours |  |  | 16 | 12 | 8 | 4 | 0
Actual - Remaining effort in uninterrupted working hours |  |  | 16 | 10 | 5 | 6 | 0
Sprint 3
Project | Story | Task | Start | Day 1 | Day 2 | Day 3 | Day 4
e-VMOL | Isi Slide-slide pelengkap VMOL | Slide Target Bisnis VMOL | 3 | 3 | 1 | 1 | 0
e-VMOL | Edit Keterangan Slide | Keterangan ditambahkan | 3 | 2 | 1 | 1 | 0
e-VMOL | Membuat Scratch Sederhana dari VMOL | Scratch VMOL | 6 | 3 | 3 | 2 | 3
e-VMOL | Edit CSS Style VMOL | Edit CSS slide | 4 | 3 | 2 | 1 | 0
Ideal - Remaining effort in uninterrupted working hours |  |  | 16 | 12 | 8 | 4 | 0
Actual - Remaining effort in uninterrupted working hours |  |  | 16 | 11 | 7 | 5 | 3
Sprint 4
Project | Story | Task | Start | Day 1 | Day 2 | Day 3 | Day 4
e-VMOL | Design VMOL | Membuat Scratch/BluePrint | 7 | 5 | 2 | 0 | 0
e-VMOL |  | Diskusi Scratch | 4 | 2 | 0 | 0 | 0
e-VMOL |  | Design & Implementation Scratch | 7 | 3 | 3 | 4 | 0
e-VMOL | Edit Style CSS VMOL & Penambahan/Pengeditan untuk Slide | Edit CSS Style & Edit Slide | 4 | 2 | 1 | 1 | 0
Ideal - Remaining effort in uninterrupted working hours |  |  | 22 | 18 | 14 | 10 | 6
Actual - Remaining effort in uninterrupted working hours |  |  | 22 | 12 | 6 | 5 | 0